## Sheet1
Page Name |  |  |  |  | Complete (Implemented in ACM) | WAG (days)
Home Page |  |  |  |  | Y
FAQ | [5 empty] | 2
Create Account |  |  |  |  | Y
Login |  |  |  |  | Y
My Account
Account Activity
Show Family Schedule
|  |  | Family Member Schedule Search page |  |  | 6
|  |  | Show Schedule |  |  | 4
List Prior Transactions
|  |  | Search for Transactions |  |  | 6
|  |  | List Transactions |  |  | 4
Transaction needed attetion
|  |  | Transaction Details |  |  | 3
|  |  | Checklist Item Detail |  |  | 3
|  |  | Receipt Details |  |  | 2
Scholarship Lists
|  |  | Scholarship Lists |  |  | 3
|  |  | Scholarship Detail |  |  | 2
Credit Cards
|  |  | List Credit Cards |  |  | 3
|  |  | Credit Card Detail |  |  | 3
|  | Show Wish List |  |  |  | 4
|  | Print Waivers |  |  |  | 4
|  | Print Tax Receipts |  |  |  | 4
|  | Print Confirmation Cards |  |  |  | 4
|  | List Program Grades |  |  |  | 3
|  | List Activity Grades |  |  |  | 3
|  | List Gift Certificates |  |  |  | 3
|  | List Deposits |  |  |  | 3
|  | List Credits |  |  |  | 3
Personal Information
|  | Change Password |  |  |  | 3
|  | Change Personal Information |  |  |  | 6
Change Question Answers
|  |  | Question Answer Lists |  |  | 5
|  |  | Answer Detail Page |  |  | 3
Change Family Information
|  |  | Family List |  |  | 3
|  |  | Add New Family |  |  | 6
|  |  | Update Family Member |  |  | 6
|  |  | Change Family Member Authorized Pickups |  |  | 5
|  | Evaulate Skills |  |  |  | 3
Account Payments
Pay on Account
|  |  | Outstanding Payment Plan List |  |  | 6
|  |  | Payment Information Page |  |  | 3
|  |  | Add Payment to Cart |  |  | 12
List of Account Payments
|  |  | Account Payments |  |  | 4
View Account Payment Details
|  |  | Payment Search Page |  |  | 4
|  |  | Payment List Page |  |  | 3
Change Auto-Charge Payments
|  |  | Payment List |  |  | 3
|  |  | Modify Auto-Charge Payment |  |  | 4
|  | Change Backup Payment Setup |  |  |  | 4
Other Services
View/Search Coupons
|  |  | List Coupons |  |  | 5
|  |  | Check Availability |  |  | 3
View Gift Certificates
|  |  | Gift Certificate List |  |  | 4
|  |  | Gift Certificate Keyword Search |  |  | 3
Modify Reservation
|  |  | Permit Search |  |  | 6
|  |  | Permit List |  |  | 3
|  |  | Permit Contract |  |  | 6
|  |  | Reservation List |  |  | 3
|  |  | Cancel Permit |  |  | 3
Modify Permit
|  |  |  | Event Lists |  | 3
|  |  |  | Event Detail |  | 4
|  |  |  | Modify Permit Schedule |  | 6
Team Management
Manage Teams
|  |  | Team List |  |  | 4
|  |  | Edit Team Details |  |  | 4
Team Members
|  |  |  | Team Member List |  | 4
|  |  |  | Withdraw Member |  | 6
|  |  |  | Edit Registration |  | 8
|  |  |  | Team Member Detail |  | 4
|  |  |  | Edit Member Detail |  | 4
|  | Enter Scores |  |  |  | 5
|  | Team Roll-Over |  |  |  | 20
League Official
|  | View Schedule |  |  |  | 4
Organization Information
|  | Manage Organization |  |  |  | 4
|  | Manage Contracts |  |  | Y
Private Lessons
|  | Book Private Lessons |  |  |  | 20
Instructor Services
|  | Private Lesson Bookings |  |  |  | 5
|  | Roster Brief |  |  |  | 4
|  | Roster Brief with Payments |  |  |  | 4
|  | Roster Expanded |  |  |  | 4
|  | Attendance Sheet |  |  |  | 4
|  | Attendance Daily |  |  |  | 4
|  | Email Participants |  |  |  | 15
Enter Pass/Fail
|  |  | Search Activities |  |  | 5
|  |  | Search Enrollee |  |  | 3
|  |  | Update Grade |  |  | 4
|  | Enter Attendance |  |  |  | 15
|  | Instructor Attedance |  |  |  | 5
|  | Edit Participant Skills |  |  |  | 8
|  | Payment Due |  |  |  | 5
|  | Payment History |  |  |  | 5
|  | Make-up Classes Reports |  |  |  | 4
|  | Available Hours |  |  |  | 6
View Bookings
|  |  | Date Range Search |  |  | 5
|  |  | Booking List |  |  | 3
Activity List
| Activity List |  |  |  | Y
| Category Landing Page |  |  |  | Y
| Calendar View |  |  |  |  | 15
| Map View |  |  |  | Y
Simple Registration
|  | Select Participant |  |  | Y
|  | Add Family Member |  |  | Y
|  | Additional Information |  |  | Y
Fee Page
|  |  | Fee page |  | Y
|  |  | Setup Payment Plan |  | Y
|  |  | Add Donation |  | Y
|  |  | Add Merchandise |  | Y
Private Lesson Registration
|  | Select Participant |  |  |  | 3
|  | Add Family Member |  |  |  | 3
|  | Book Lessons |  |  |  | 20
|  | Additional Information |  |  |  | 5
Fee Page
|  |  | Fee Page |  |  | 3
|  |  | Setup Payment Plan |  |  | 8
|  |  | Add Donation |  |  | 3
|  |  | Add Merchandise |  |  | 3
Team Registration (for a team)
|  | Team Manager |  |  |  | 5
|  | Create Team |  |  |  | 5
|  | Invite Members |  |  |  | 5
|  | Confirmation |  |  |  | 3
Team Registration (for an individual)
|  | Select Participant |  |  | Y
|  | Add Family Member |  |  | Y
|  | Select Team |  |  | Y
|  | Create Team |  |  | Y
|  | Additional Information |  |  | Y
Fee Page
|  |  | Fee Page |  | Y
|  |  | Setup Payment Plan |  | Y
|  |  | Add Donation |  | Y
|  |  | Add Merchandise |  | Y
Package Registration
|  | Select Participant |  |  |  | 3
|  | Add Family Member |  |  |  | 3
|  | Package Items |  |  |  | 10
|  | Additional Info For Each Item |  |  |  | 5
Fee page
|  |  | Fee Page |  |  | 10
|  |  | Setup Payment Plan |  |  | 5
|  |  | Add Donation |  |  | 3
|  |  | Add Merchandise |  |  | 3
FlexReg Registration
|  | Select Participant |  |  |  | 5
|  | Add Family Member |  |  |  | 5
|  | Review Program |  |  |  | 10
|  | Date/Session Selection |  |  |  | 20
|  | Additional Information |  |  |  | 5
Fee Page
|  |  | Fee Page |  |  | 10
|  |  | Setup Payment Plan |  |  | 10
|  |  | Add Donation |  |  | 5
|  |  | Add Merchandise |  |  | 5
Cart
| Entry in Cart |  |  |  | Y
| Add Another |  |  |  | Y
| Remove Item |  |  |  | Y
| Edit Item |  |  |  | Y
Outstanding Balances Page
|  | Outstanding Balances Page |  |  |  | 8
|  | Account Balance Detail |  |  |  | 8
|  | Outstanding Balances Confirmation Page |  |  |  | 4
| Order Confrimation (Waivers) |  |  |  | Y
| Payment Information |  |  |  | Y
| Future Payment |  |  |  | Y
| Active Advantage Offer |  |  |  | Y
| Magazine Offer |  |  |  | Y
| Order Confirmation Page |  |  |  | Y
| Receipt Page |  |  |  | Y
Membership List
| Membrership List |  |  |  | Y
| View Details |  |  |  | Y
Membership Purchase
|  | Number of Period Selection |  |  |  | 5
|  | Select Participant |  |  |  | 8
|  | Additional Information |  |  |  | 5
Fee Page
|  |  | Fee Page |  |  | 5
|  |  | Setup Payment Plan |  |  | 5
|  |  | Add Donation |  |  | 3
|  |  | Add Merchandise |  |  | 3
Membership Renewal
|  | Additional Information |  |  |  | 5
Fee Page
|  |  | Fee Page |  |  | 5
|  |  | Setup Payment Plan |  |  | 3
|  |  | Add Donation |  |  | 3
|  |  | Add Merchandise |  |  | 3
Campaign List
| Campaign List |  |  |  |  | 5
Campaign Detail
|  | Campaign Detail |  |  |  | 15
|  | Campaign Add to Cart |  |  |  | 10
Gift Certificate List
| Gift Certificate List |  |  |  |  | 8
| Gift Certificate Detail |  |  |  |  | 5
Gift Certificate Purchase
|  | Select Participant |  |  |  | 10
|  | Fee Page |  |  |  | 5
League List
| League List |  |  |  |  | 15
League Schedules
|  | League Schedule Detail |  |  |  | 5
|  | League Contacts |  |  |  | 5
Teams
|  |  | Teams |  |  | 5
|  |  | Team Contacts |  |  | 5
|  |  | Schedules |  |  | 5
|  |  | Scores |  |  | 5
Schedules
|  |  | Schedules |  |  | 5
|  |  | Facility Detail |  |  | 2
|  | Scores |  |  |  | 5
|  | Standing |  |  |  | 5
|  | Notes |  |  |  | 3
Reservation Options
| Option page |  |  |  | Y
Facility Lists
View Booking Calendar
|  |  | Booking Calendar |  |  | 15
|  |  | Select Date/Time |  |  | 15
|  |  | Reserve Faacility |  |  | 10
|  |  | Reservation Details |  |  | 15
View Details
|  |  | Detail Page |  |  | 10
|  |  | Check Availability |  |  | 15
|  |  | Reserve Facility |  |  | 10
|  |  | Reservation Details |  |  | 15
Reservation Request (Permit)
|  | Select Event Type/Enter Description/# guests |  |  |  | 10
|  | Facility Equipemnt Search |  |  |  | 15
|  | Enter Dates/Time Duration |  |  |  | 8
|  | Review/Change Dates |  |  |  | 10
|  | Reservation Availability |  |  |  | 8
|  | Select Facility Time |  |  |  | 8
|  | Reservation Checklist/Questions |  |  |  | 10
|  | Review Reservation |  |  |  | 8
|  | Payment |  |  |  | 15
Quick Reserve
|  | Check Availability |  |  |  | 20
|  | Select Facility |  |  |  | 15
|  | Reservation Details |  |  |  | 15
|  | Payment |  |  |  | 15
Location Maps List
|  | Maps List |  |  | Y
|  | View Location Map |  |  |  | 15
|  | Select Facility |  |  |  | 8
|  | Reserve |  |  |  | 15
|  | Reserve Details |  |  |  | 10
|  | Reservation Checklist/Questions |  |  |  | 10
|  | Reservation Review |  |  |  | 8
|  | Pyament |  |  |  | 15
Equipment List
|  | Equipment Type List |  |  |  | 5
|  | Equipment List |  |  |  | 5
|  | Equipment Detail |  |  |  | 5
Locker Room List
|  |  | List Page |  |  | 5
|  |  | View Lockers |  |  | 15
|  |  | Select Locker |  |  | 15
|  |  | Reserve |  |  | 10
|  |  | Reservation Details |  |  | 10