## Sheet1
Task | WAG (hr) AUI + Legacy CUI | AUI + ACM CUI | No AUI w ACM CUI | No AUI w Legacy CUI | AUI w Legacy CUI | translator support | All Reports | Phase 1
Framework proof of concept work
Global configuration: License key, supported language key configuration | 16 | 16 | 16 | 16 | 16 |  |  | 16
Language changer on HTML and CUI pages | 16 | 8 | 8 | 8 | 16 |  |  | 16
HTML tokenization proof of concept: Tokenization of one page: Default language resource file, alternate language resource file, org override table, token resolution method and de-tokenization of HTML | 80 | 60 | 60 | 60 | 80 |  |  | 80
Proof of concept of ACM static localization: Servlet token resolution WS API, custom control text resolution via API | 40 | 40 | 40 | 40 | 40 |  |  | 40
Proof of concept of applet tokenization: One label customized | 16 | 0 | 0 | 0 | 16 |  |  | 16
Proof of concept of Flex tokenization | 16 | 0 | 0 | 0 | 16 |  |  | 16
Proof of concept of receipt static text tokenization: One label customized | 16 | 0 | 0 | 0 | 16 |  |  | 16
Proof of concept of DB localization in servlet: Activity name: Companion table, caching, default language display; multi-lingual editing. | 80 | 80 | 80 | 80 | 80 |  |  | 80
Proof of concept of DB localization in CUI: Activity name: WS method changes for localized text, language-specific text displayed. (Caching) | 60 | 60 | 60 | 60 | 60 |  |  | 60
Proof-of-concept of DB localization in applet | 16 | 16 |  |  | 16 |  |  | 16
Proof of concept for receipt DB localization: sending language to report, using view | 32 | 32 |  |  | 32 |  |  | 32
Proof of concept of code-resident text resolution (e.g., error messages) | 8 | 8 | 8 | 8 | 8 |  |  | 8
Framework buildout
Servlet session language control: customer login, system user login, | 32 | 32 |  |  | 32 |  |  | 32
ACM session language control: customer login, system user login, language sync with servlet | 32 | 32 | 32 | 32 | 32 |  |  | 32
Tokenization utility for HTML | 120 | 120 |  | 120 | 120 |  |  | 120
Servlet automatic creation of default language resource entries | 16 | 16 | 16 | 16 | 16 |  |  | 16
All existing CUI custom controls re-route to servlet tokenization | 40 | 40 | 40 | 40 | 40 |  |  | 40
Upsizer support for DB localization | 32 | 32 | 32 | 32 | 32 |  |  | 32
Tabular editor for org override text | 24 | 24 | 24 | 24 | 24 |  |  | 24
Servlet in-place editor for org override text (static text) | 80 |  |  |  | 80 | 80
CUI in-place editor for org override text (static text) | 80 | 80 | 80 | 80 | 80 | 80
Servlet in-place editor for static translation (optional?) | 60 |  |  |  | 60 | 60
CUI in-place editor for static translation (optional?) | 60 | 60 | 60 | 60 | 60 | 60
CUI caching of tokenized static text by org/token/language | 80 | 80 | 80 | 80 | 80 |  |  | 80
Allocation to invest in tools for locating / tokenizing text in code. | 80 | 80 | 80 | 80 | 80 |  |  | 80
Multi-lingual asset service support
Bulk work
Servlet pages: test and fix any problems resulting from tokenization utility | 60 | 60 |  |  | 60
2786 files
264890 lines
Conversion of all existing CUI pages to use custom controls | 80 | 80 | 80 | 80 | 80
Complete tokenization of static text in applets | 80 | 80 |  |  | 80
Complete tokenization of static text in Flex | 80 | 80 |  |  | 80
Servlet modifications for all DB localization | 480 | 480 | 480 | 480 | 480
120 fields * 4h = 480
CUI modifications for all DB localization | 208 | 208 | 208 | 208 | 208
(for displaying French activity name etc)
100 fields * 2h = 200
10 types of assets, change data type to list of String: 8
Flex modifications for all DB localization | 80 | 80 |  |  | 80
Applet modifications for all DB localization | 60 | 60 |  |  | 60
Servlet: Embedded text | 240 | 240 |  |  | 240
p.put(String) 3286 usages
p.put(StringBuilder) 189 usages
CUI embedded text | 80 | 80 | 80 | 80 | 80
Receipt static text localization | 8 | 8 | 8 | 8 | 8
Permit static text localization | 8 | 8 | 8 | 8 | 8
Statement static text localization | 8 | 8 | 8 | 8 | 8
? Pass printing report change | 8 | 8 | 8 | 8 | 8
? DB localization of 4 reports (using views in reports) | 40 | 40 | 40 | 40 | 40
? DB localization of all reports (using views in reports) | 400 | 400 |  |  |  |  | 400
? Static localization of all reports | 400 | 400 |  |  |  |  | 400
Initial translation of resource file into French
Initial translation of resource file into Spanish
Implement All CUI pages natively in ACM (+ Mobile support) |  | 9648 | 9648
Total Hour | 3452 | 12884 | 11284 | 1756 | 2652 | 280 | 800 | 852